## Risk Brainstorming
BrainStorming
Department | Key elements | Construction processes / Factors | Identified Risks | Current Risk Management methods | Proposed Risk Management methods
Project Management | Planning & scheduling | Project timeline, Sequencing of activities | Schedule delays due to poor planning or coordination | Baseline schedule, Weekly progress meetings | Use Primavera/MS Project with critical path analysis, look-ahead planning (3–6 weeks)
| Cost Control | Budgeting, Cash flow | Cost overrun due to inaccurate BOQ or price escalation | Initial cost estimate, approval workflow | Detailed cost breakdown (CBS), contingency reserves, periodic cost variance analysis
Site Operations | Excavation & Earthworks | Soil conditions | Collapse of excavation sides | Basic shoring and supervision | Geotechnical investigation, engineered shoring systems
| Concrete Works | Mixing, pouring, Curing | Poor concrete quality | Site supervision, cube testing | Automated batching control, curing procedures & checklists

## Risk Assesment(Planning&schedu)
Severity Of Risk
|  | Key elements | Risk | 1 | 2 | 3 | 4 | 5 | Number of occuraneces | Likelihood
M1 | Week 1 | Planning & scheduling | Schedule delays due to poor planning or coordination | [5 empty] | 5 | 0.067568
| Week 2 | [7 empty] | 7 | 0.094595
| Week 3 | [7 empty] | 6 | 0.081081
| Week 4 | [7 empty] | 3 | 0.040541
M2 | Week 1 | [7 empty] | 4 | 0.054054
| Week 2 | [7 empty] | 2 | 0.027027
| Week 3 | [7 empty] | 2 | 0.027027
| Week 4 | [7 empty] | 10 | 0.13514
M3 | Week 1 | [7 empty] | 9 | 0.12162
| Week 2 | [7 empty] | 10 | 0.13514
| Week 3 | [7 empty] | 7 | 0.094595
| Week 4 | [7 empty] | 9 | 0.12162
[9 empty] | 74 | 3.378%

## Weibull(Planning & Schedule)
|  | X | Step1 | Step2 | Step3
| Weeks | Number of occurances | Rank | X-axis | Y-axis | Excel Weibull function
M1 | Week1 | 5 | 5 | -0.74134 | 1.6094 | Weibull Slope α | 2.0493 | Step4 |  | Exponential
| Week2 | 7 | 7 | -0.25202 | 1.9459 | β | 7.464 | Step5 | Mean (average) | EXPONDIST()
| Week3 | 6 | 6 | -0.48518 | 1.7918 | Weibull, CDF | 83.81% | Step6 | 6.1667 | 80.24%
| Week4 | 3 | 3 | -1.4042 | 1.0986
M2 | Week1 | 4 | 4 | -1.0374 | 1.3863
| Week2 | 2 | 1 | -2.8455 | 0.69315 | Weibull (CDF) defines the cumulative percentage of price that will occur at time t
| Week3 | 2 | 1 | -2.8455 | 0.69315
| Week4 | 10 | 11 | 0.68666 | 2.3026
M3 | Week1 | 9 | 9 | 0.19009 | 2.1972
| Week2 | 10 | 11 | 0.68666 | 2.3026
| Week3 | 7 | 7 | -0.25202 | 1.9459
| Week4 | 9 | 9 | 0.19009 | 2.1972
| EXPECTED | 10.031
| Expected Number of occurances using Weibull | 10.031
| Expected Number of occurances using Exponential | 8.5488
| Standard Deviation | 2.8529
| Action Limit (99%) | 10.7218
| Normal Limit (99%) | 9.3401

## Risk Assesment(Cost Control)
Severity Of Risk
|  | Key elements | Risk | 1 | 2 | 3 | 4 | 5 | Number of occuraneces | Likelihood
M1 | Week 1 | Cost Control | Cost overrun due to inaccurate BOQ or price escalation | [5 empty] | 11 | 0.12088
| Week 2 | [7 empty] | 8 | 0.087912
| Week 3 | [7 empty] | 6 | 0.065934
| Week 4 | [7 empty] | 11 | 0.12088
M2 | Week 1 | [7 empty] | 9 | 0.098901
| Week 2 | [7 empty] | 4 | 0.043956
| Week 3 | [7 empty] | 6 | 0.065934
| Week 4 | [7 empty] | 7 | 0.076923
M3 | Week 1 | [7 empty] | 8 | 0.087912
| Week 2 | [7 empty] | 3 | 0.032967
| Week 3 | [7 empty] | 7 | 0.076923
| Week 4 | [7 empty] | 11 | 0.12088
[9 empty] | 91 | 2.289%

## Weibull(Cost Control)
|  | X | Step1 | Step2 | Step3
| Weeks | Number of occurances | Rank | X-axis | Y-axis | Excel Weibull function
M1 | Week1 | 11 | 10 | 0.42163 | 2.3979 | Weibull Slope α | 2.6303 | Step4 |  | Exponential
| Week2 | 8 | 7 | -0.25202 | 2.0794 | β | 9.1686 | Step5 | Mean (average) | EXPONDIST()
| Week3 | 6 | 3 | -1.4042 | 1.7918 | Weibull, CDF | 80.1% | Step6 | 7.5833 | 76.56%
| Week4 | 11 | 10 | 0.42163 | 2.3979
M2 | Week1 | 9 | 9 | 0.19009 | 2.1972
| Week2 | 4 | 2 | -1.9142 | 1.3863 | Weibull (CDF) defines the cumulative percentage of price that will occur at time t
| Week3 | 6 | 3 | -1.4042 | 1.7918
| Week4 | 7 | 5 | -0.74134 | 1.9459
M3 | Week1 | 8 | 7 | -0.25202 | 2.0794
| Week2 | 3 | 1 | -2.8455 | 1.0986
| Week3 | 7 | 5 | -0.74134 | 1.9459
| Week4 | 11 | 10 | 0.42163 | 2.3979
| EXPECTED | 10.987
| Expected Number of occurances using Weibull | 10.987
| Expected Number of occurances using Exponential | 10.5127
| Standard Deviation | 2.5317
| Action Limit (99%) | 11.6001
| Normal Limit (99%) | 10.3739

## Risk Assesment(Excavation)
Severity Of Risk
|  | Key elements | Risk | 1 | 2 | 3 | 4 | 5 | Number of occuraneces | Likelihood
M1 | Week 1 | Excavation & Earthworks | Collapse of excavation sides | [5 empty] | 12 | 0.11215
| Week 2 | [7 empty] | 8 | 0.074766
| Week 3 | [7 empty] | 9 | 0.084112
| Week 4 | [7 empty] | 7 | 0.065421
M2 | Week 1 | [7 empty] | 6 | 0.056075
| Week 2 | [7 empty] | 12 | 0.11215
| Week 3 | [7 empty] | 16 | 0.14953
| Week 4 | [7 empty] | 7 | 0.065421
M3 | Week 1 | [7 empty] | 8 | 0.074766
| Week 2 | [7 empty] | 3 | 0.028037
| Week 3 | [7 empty] | 3 | 0.028037
| Week 4 | [7 empty] | 16 | 0.14953
[9 empty] | 107 | 3.18%

## Weibull(Excavation)
|  | X | Step1 | Step2 | Step3
| Weeks | Number of occurances | Rank | X-axis | Y-axis | Excel Weibull function
M1 | Week1 | 12 | 9 | 0.19009 | 2.4849 | Weibull Slope α | 2.201 | Step4 |  | Exponential
| Week2 | 8 | 6 | -0.48518 | 2.0794 | β | 10.8193 | Step5 | Mean (average) | EXPONDIST()
| Week3 | 9 | 8 | -0.030321 | 2.1972 | Weibull, CDF | 90.61% | Step6 | 8.9167 | 83.38%
| Week4 | 7 | 4 | -1.0374 | 1.9459
M2 | Week1 | 6 | 3 | -1.4042 | 1.7918
| Week2 | 12 | 9 | 0.19009 | 2.4849 | Weibull (CDF) defines the cumulative percentage of price that will occur at time t
| Week3 | 16 | 11 | 0.68666 | 2.7726
| Week4 | 7 | 4 | -1.0374 | 1.9459
M3 | Week1 | 8 | 6 | -0.48518 | 2.0794
| Week2 | 3 | 1 | -2.8455 | 1.0986
| Week3 | 3 | 1 | -2.8455 | 1.0986
| Week4 | 16 | 11 | 0.68666 | 2.7726
| EXPECTED | 15.804
| Expected Number of occurances using Weibull | 15.804
| Expected Number of occurances using Exponential | 12.3611
| Standard Deviation | 4.1525
| Action Limit (99%) | 16.8096
| Normal Limit (99%) | 14.7984

## Risk Assesment(Concrete Works)
Severity Of Risk
|  | Key elements | Risk | 1 | 2 | 3 | 4 | 5 | Number of occuraneces | Likelihood
M1 | Week 1 | Concrete Works | Poor concrete quality | [5 empty] | 6 | 0.072289
| Week 2 | [7 empty] | 9 | 0.10843
| Week 3 | [7 empty] | 7 | 0.084337
| Week 4 | [7 empty] | 4 | 0.048193
M2 | Week 1 | [7 empty] | 7 | 0.084337
| Week 2 | [7 empty] | 5 | 0.060241
| Week 3 | [7 empty] | 12 | 0.14458
| Week 4 | [7 empty] | 10 | 0.12048
M3 | Week 1 | [7 empty] | 9 | 0.10843
| Week 2 | [7 empty] | 7 | 0.084337
| Week 3 | [7 empty] | 3 | 0.036145
| Week 4 | [7 empty] | 4 | 0.048193
[9 empty] | 83 | 2.527%

## Weibull(Concrete works)
|  | X | Step1 | Step2 | Step3
| Weeks | Number of occurances | Rank | X-axis | Y-axis | Excel Weibull function
M1 | Week1 | 6 | 5 | -0.74134 | 1.7918 | Weibull Slope α | 2.7417 | Step4 |  | Exponential
| Week2 | 9 | 9 | 0.19009 | 2.1972 | β | 8.1199 | Step5 | Mean (average) | EXPONDIST()
| Week3 | 7 | 6 | -0.48518 | 1.9459 | Weibull, CDF | 48.61% | Step6 | 6.9167 | 63.65%
| Week4 | 4 | 2 | -1.9142 | 1.3863
M2 | Week1 | 7 | 6 | -0.48518 | 1.9459
| Week2 | 5 | 4 | -1.0374 | 1.6094 | Weibull (CDF) defines the cumulative percentage of price that will occur at time t
| Week3 | 12 | 12 | 1.0558 | 2.4849
| Week4 | 10 | 11 | 0.68666 | 2.3026
M3 | Week1 | 9 | 9 | 0.19009 | 2.1972
| Week2 | 7 | 6 | -0.48518 | 1.9459
| Week3 | 3 | 1 | -2.8455 | 1.0986
| Week4 | 4 | 2 | -1.9142 | 1.3863
| EXPECTED | 7.0291
| Expected Number of occurances using Weibull | 7.0291
| Expected Number of occurances using Exponential | 9.5885
| Standard Deviation | 2.5967
| Action Limit (99%) | 7.658
| Normal Limit (99%) | 6.4002

## Risk score
Identified Risk | Probability (p) | Likelihood (L) | Risk Score (P * L) | Rank
Risk (Planning & schedule) | 83.81% | 3.378% | 0.028315 | 3
Risk ( Cost Control) | 80.1% | 2.289% | 0.018338 | 2
Risk (Excavation) | 90.61% | 3.18% | 0.028817 | 4
Risk (Concrete works) | 48.61% | 2.527% | 0.012283 | 1