CONFIDENTIAL // INDEPENDENT FORENSIC & TECHNICAL AUDIT

TALAAT MOUSTAFA GROUP HOLDING
(EGX: TMGH.CA)

Comprehensive Forensic Due Diligence & Technical Audit Report
Financial Engineering, Contractual Privity, Supply Chain Solvency, and Mega-Project Execution Risks

## Table 1: Key Executive Forensic Due Diligence Metrics

| Metric / Financial Indicator | Audited Value / Quantum | Forensic Verification Source | Audit Interpretation |
| --- | --- | --- | --- |
| Issued & Paid-in Share Capital | EGP 20,635,600,000 (2.063B shares) | Official EGX Filings / Commercial Register | Unchanged since 2007; nominal value EGP 10.00/shr |
| Consolidated Assets (FY2025 Audited) | EGP 410,900,000,000 (410.9 Billion) | Audited EAS Consolidated Financial Statements | Massive expansion driven by land revaluation & ADQ hotel deal |
| Effective Consolidated Liabilities | EGP 238,200,000,000 (238.2 Billion) | On-Balance (194.2B) + Off-Balance Lease (44.0B) | Structural liability profile dominated by customer prepayments |
| Central Treasury Liquid Float | EGP 47,000,000,000 (47.0 Billion) | Bank Term Deposits & Treasury Bills | Core liquidity reserve insulated at holding company level |
| Unearned Customer Prepayment Backlog | EGP 129,000,000,000 (Balance Sheet Float) | Off-Plan Client Advance Collections | Mandatory future construction liability; non-financial debt |
| Trade & Subcontractor Payables | EGP 15,790,000,000 (15.79 Billion) | Verified Balance Sheet Notes Payable | Supply chain float buffering TMG working capital requirements |
| Master Strategic Landbank Reserve | 74,000,000+ sqm (17,600+ feddans) | Title Deeds, NUCA Decrees & Royal Allocations | Largest private strategic urban reserve in MENA region |
| Active Supply Chain Corporate Network | 42 Verified Prime Corporate Entities | Commercial Registry & Forensic Project Filings | Multi-tier contractor network executing civil/MEP packages |

## Table 2: Strategic Mega-Projects Portfolio

| Project Name | Land Area | Spatial Location | Concession & Land Framework | Primary Engineering Scope | Key Execution Contractors |
| --- | --- | --- | --- | --- | --- |
| Madinaty | 8,000 feddans (33.6M sqm) | East Cairo Corridor (Suez Rd Km 33) | NUCA In-Kind Barter Agreement (7% built space) | Integrated smart city, 120,000 units, golf courses, central spine | ACC, Concrete Plus, MCBS, Orion FM |
| Noor City | 5,000 feddans (21.0M sqm) | Capital Gardens (Opposite New Capital) | NUCA In-Kind Sharing Agreement (Fixed sqm allocation) | Next-generation AI smart city, 140,000 residential units, green corridors | ACC, Atrium, Hassan Allam Utilities |
| SouthMed | 5,542 feddans (23.3M sqm) | Mediterranean Coast (Dabaa Km 165-170) | Direct Private Acquisition & State Concession | Ultra-luxury coastal city, 107km crystal lagoons, international marina | Concrete Plus, Metito, P.Zone Intl |
| Celia | 500 feddans (2.1M sqm) | New Administrative Capital (R3 Zone) | Direct Master Tender Land Allocation | Premium residential compound, luxury high-rises, cultural park | ACC, Specialized Subcontractors |
| Banan City | 1,666 feddans (7.0M sqm) | Riyadh, Kingdom of Saudi Arabia (Al Fursan) | National Housing Company (NHC) Revenue Share | 27,000 integrated villas and apartments, regional headquarters | TMG KSA, Thabat Contracting |
| Jood & Muscat | Hospitality & Mixed-Use | Muscat, Sultanate of Oman | Bilateral Ministerial Tourism Concession | Four Seasons resort, branded residences, coastal leisure infrastructure | ICON Hospitality JV Partners |

## Table 4: Audited Consolidated Balance Sheet

| Balance Sheet Line Item | FY2021 | FY2022 | FY2023 | FY2024 | FY2025 | Common Size % (25) |
| --- | --- | --- | --- | --- | --- | --- |
| Cash & Bank Equivalents | 4,210 | 4,780 | 11,500 | 32,000 | 47,000 | 11.4% |
| Accounts & Notes Receivable | 24,500 | 28,600 | 36,400 | 48,200 | 68,500 | 16.7% |
| Real Estate Work in Progress (WIP) | 46,800 | 54,200 | 71,300 | 102,500 | 154,200 | 37.5% |
| Financial Investments at Fair Value | 1,521 | 2,100 | 4,200 | 8,500 | 14,800 | 3.6% |
| Fixed Assets & Hotel Properties (CWIP) | 31,200 | 36,800 | 51,200 | 81,400 | 114,600 | 27.9% |
| Other Current & Non-Current Assets | 3,470 | 3,920 | 4,620 | 6,200 | 11,800 | 2.9% |
| TOTAL CONSOLIDATED ASSETS | 111,701 | 130,400 | 179,220 | 278,800 | 410,900 | 100.0% |
| Bank Overdrafts & Short-Term Facilities | 3,800 | 4,500 | 6,200 | 8,900 | 12,400 | 3.0% |
| Trade & Notes Payable (Supply Chain) | 5,120 | 7,300 | 9,800 | 13,500 | 15,790 | 3.8% |
| Customer Advances & Unearned Booking Float | 38,500 | 48,200 | 72,000 | 95,000 | 129,000 | 31.4% |
| Long-Term Bank Debt | 8,200 | 9,800 | 14,500 | 19,800 | 28,700 | 7.0% |
| Off-Balance Sheet Synthetic Lease Debt | 1,200 | 2,100 | 4,800 | 22,100 | 44,000 | 10.7% |
| Other Provisions & Operational Liabilities | 2,140 | 2,600 | 3,630 | 4,730 | 8,310 | 2.0% |
| TOTAL CONSOLIDATED LIABILITIES | 58,960 | 74,500 | 110,930 | 164,030 | 238,200 | 58.0% |
| Paid-in Share Capital | 20,636 | 20,636 | 20,636 | 20,636 | 20,636 | 5.0% |
| Legal & Translation Reserves | 3,450 | 4,100 | 5,200 | 7,800 | 14,200 | 3.5% |
| Retained Earnings | 28,655 | 31,164 | 42,454 | 52,834 | 78,364 | 19.1% |
| Non-Controlling Interests (ADQ ICON Equity) | 0 | 0 | 0 | 33,500 | 59,500 | 14.5% |
| TOTAL SHAREHOLDERS' EQUITY | 52,741 | 55,900 | 68,290 | 114,770 | 172,700 | 42.0% |
| TOTAL LIABILITIES & EQUITY | 111,701 | 130,400 | 179,220 | 278,800 | 410,900 | 100.0% |

## Table 8: Mustakhlasat (IPC) 7-Stage Payment Verification Cycle

| Audit Gate & Process Description | Contractual Target | Forensic Actual | Responsible Audit Authority | Primary Operational Friction & Contractor Risk |
| --- | --- | --- | --- | --- |
| Stage 1: Field Site Measurement & Joint Verification | 14 Days | 35 Days | Subcontractor QS & ACC Field Engineer | Physical disputes over completed earthworks, formwork, and rough MEP testing sign-offs. Work continues on contractor balance sheet without interim certificate recognition. |
| Stage 2: Technical Office Reconciliation & BOQ Audit | 14 Days | 45 Days | ACC / Atrium Central Technical Office | Aggressive unit price slashing against tender specs; reclassification of variations as base scope. Deductions averaging 12% to 22% applied retroactively to gross invoiced volume. |
| Stage 3: Supervising Consultant Certification | 14 Days | 30 Days | Independent Consultant (ACE / Hill Int.) | Batching submissions to prevent consultant fee overruns; rigid QA/QC non-conformance holdbacks. Material holdbacks of 10% retained pending final lab batch compression tests. |
| Stage 4: TMG Internal Audit & Cost Control Scrutiny | 14 Days | 50 Days | TMG Holding Cost Control & Forensic Audit Panel | Cash disbursement rationing; audit reviews cross-check previous advance payment amortization. Advance payment deductions applied ahead of contractual milestone schedule. |
| Stage 5: Executive Management Approval & Cheque Issuance | 14 Days | 40 Days | Managing Director & Central Treasury | Approval cycles queued against centralized monthly corporate cash collections. Cheques drawn on post-dated 60 to 90-day banking instruments rather than spot wire transfer. |
| Stage 6: Commercial Paper Liquidation & Bank Clearing | 10 Days | 45 Days | National Bank of Egypt / Banque Misr | Liquidity rationing on notes payable; contractor forced to discount paper at 24% annual yield. Contractor realizes effective 6% to 8% margin loss to obtain immediate liquidity. |
| Stage 7: Retention Release & Defect Liability Clearance | 10 Days | 25 Days | TMG Facilities Management (Orion) & Asset SPV | Handover snags inflated to offset final 5% retention liability against vendor. Final 5% to 10% retention withheld indefinitely or negotiated down by 50%. |

## Table 10: Weibull Quantitative Failure Modeling

| Forensic Risk Pillar | Shape (β) | Scale (η) | 12-Month Failure | 24-Month Failure | 36-Month Failure | Mean Time (MTTF) | Primary Hazard & Failure Dynamic |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Supply Chain & Material Cost Inflation | 2.85 | 14.2 mos | 42.8% | 88.6% | 99.4% | 12.6 mos | Rapid wear-out / FX devaluation pass-through causing supplier insolvency |
| Contractual Privity & Litigation Ring-Fencing | 1.35 | 38.5 mos | 18.2% | 41.5% | 62.8% | 35.2 mos | Constant failure hazard; CRCICA arbitration friction and lien defense |
| Subcontractor Working Capital Exhaustion | 3.10 | 11.8 mos | 56.4% | 94.2% | 99.8% | 10.5 mos | Extreme wear-out; 270d IPC delays deplete tier-2/3 contractor cash buffers |
| Mega-Project Infrastructure Execution Delay | 2.20 | 26.4 mos | 24.5% | 64.1% | 89.3% | 23.4 mos | Lagoon water treatment and high-voltage grid substation handover bottlenecks |
| Off-Balance Sheet Debt & Rawasy Lease Refinancing | 1.95 | 29.1 mos | 21.0% | 58.0% | 84.5% | 25.8 mos | Interest rate surge triggers lease refinancing spread expansion on EGP 44B float |
| Unearned Customer Backlog Handover Slippage | 2.60 | 22.5 mos | 31.2% | 76.8% | 96.5% | 19.9 mos | Accelerating customer cancellation hazard if delivery lags exceed 18 months |

## Table 11: Master Contractor & Supply Chain Directory (42 Entities)

| Ref ID | Corporate Contracting Entity | Assigned Project / Package | Relationship Framework | Professional Scope of Work | Corporate Contact & Registry |
| --- | --- | --- | --- | --- | --- |
| 1 | Concrete Plus for Engineering & Construction | SouthMed | Declared Direct Contract with TMG | Prime EPC Contractor: 179 Fully Finished Residential Buildings & Infrastructure (Zone C01) | +20 2 2307 6581 ¦ info@concrete-plus.net |
| 2 | Atrium Quality Contractors | Madinaty, Four Seasons Luxor, All Seasons Park | Captive Group General Contractor | General Contracting, Fit-Out & Structural Works for Commercial Malls & Luxury Hospitality | +20 2 2693 1643 ¦ info@atriumqc.com |
| 3 | P.Zone International for Contracting | Madinaty & Noor City | Specialized Subcontractor | Specialized Water Features, Artificial Lagoons & Electromechanical MEP Works | Official Commercial Registry |
| 4 | Metito | SouthMed | Water Infrastructure Partner | Seawater Desalination, Advanced Wastewater Treatment & Deep Intake Facilities | +20 2 2404 0500 ¦ egypt@metito.com |
| 5 | Hassan Allam Utilities | Noor City | Strategic Infrastructure Concession | Water Treatment, District Cooling & Power Transmission Grid Concessions | +20 2 2265 9000 ¦ utilities@hassanallam.com |
| 6 | Saveto | Group Mega-Projects | Building Materials Supplier | Pre-mixed Mortars, Finishing Plasters & Specialized Construction Chemicals | +20 2 3820 4000 ¦ info@saveto.com |
| 7 | El Soadaa Group | SouthMed | Subcontractor / Joint Works | Civil Infrastructure, Earthworks & Bridges; Documented in Vendor Meetings | +20 2 2704 1297 ¦ info@elsoadaa.com |
| 8 | Gharably Integrated Engineering Co. (GIECO) | SouthMed | Civil Marine Contractor | Marine Structures, Breakwaters, Coastal Dredging & Earthmoving Works | +20 3 429 7889 ¦ info@gieco.com.eg |
| 9 | Knauf Egypt | Four Seasons Luxor | Drywall Systems Supplier | Gypsum Boards, Sound Insulation & Specialized Drywall Ceiling Systems | +20 2 2395 2247 ¦ info@knauf.com.eg |
| 10 | DEVZAH SI | Madinaty | Specialized Materials Supplier | Architectural Finishings & Construction Hardware Delivery Delivery | Official Vendor Registry |
| 11 | Cleopatra Group (Ceramics & Sanitary) | SouthMed | Finishing Materials Supplier | Supply of Ceramic Tiles, Porcelain & Sanitary Fixtures for Residential Units | Verified Corporate Registry |
| 12 | Richmond Group Egypt | Cairo Capital Properties | Fit-out Contractor | Commercial Renovation, Aqua & Steak House Restaurant Fit-Out Works | Commercial Registry Cairo |
| 13 | Hill International | Madinaty & Four Seasons Luxor | Project Management Consultant (PMC) | Comprehensive Construction Management, Site Supervision & QA/QC Oversight | +20 2 2322 2000 ¦ cairo@hillintl.com |
| 14 | Dar Al-Handasah | Madinaty & Sharm El Sheikh | Lead Engineering Consultant | Master Planning, Structural Engineering & East Hub Mall Detailed Design | +20 2 3531 2220 ¦ info@dar.com |
| 15 | EHAF Consulting Engineers | Madinaty | Supervising Engineering Consultant | Site Supervision & Architectural Review for East Hub Commercial Mall | +20 2 3760 1099 ¦ ehaf@ehaf.com |
| 16 | ECG Engineering Consultants Group | Madinaty & Sharm El Sheikh | Lead Design & Supervision Consultant | Open Air Mall & Four Seasons Resort Detailed Engineering & MEP Supervision | +20 2 2274 4740 ¦ info@ecgsa.com |
| 17 | Shaker Consultancy Group (SCG) | Madinaty, Noor City, SouthMed | Specialized Electromechanical Consultant | MEP Infrastructure, Power Substations, High-Voltage Grids & Lighting Design | +20 2 2352 4740 ¦ info@shakerconsultancygroup.com |
| 18 | Raafat Miller Consulting (RMC) | Al Rehab, Madinaty, SouthMed | Architectural Design Consultant | Gateway Mall, All Seasons Park & TMG New Corporate Headquarters Architecture | +20 2 2587 2500 ¦ info@rmc.com.eg |
| 19 | Hamza Associates | New Capital & Madinaty | Geotechnical & Structural Consultant | Celia New Capital Foundations, Geotechnical Boreholes & Soil Stabilization | +20 2 3760 7238 ¦ info@hamza.org |
| 20 | DMA Architects / Design & Engineering | Madinaty | Architectural Consultant | Privado Gated Enclave & Luxury Villas (V24) Architectural Design | Commercial Registry Cairo |
| 21 | PME Project Management & Engineering | Al Rehab City | Project Management Consultant | Project Management & Fit-Out Supervision for Al Rehab Commercial Strip | Official Consulting Registry |
| 22 | Mimar Interiors | Four Seasons Luxor | Interior Design Consultant | Hospitality Interior Architecture, Finishes & Millwork Specifications | +20 2 3291 5923 ¦ info@mimar.ae |
| 23 | Interserve Consulting Group | Madinaty | Technical Engineering Auditor | Technical Due Diligence & Engineering Specification Verification | Corporate Engineering Registry |
| 24 | IEC Consultants | Madinaty | Engineering Verification Consultant | Structural Safety Auditing & Material Compliance Inspection | Official Consulting Directory |
| 25 | ENDEL Egypt | Four Seasons Cairo Capital | MEP Package Contractor | HVAC, Electromechanical Plant & Firefighting Package CP03 Execution | +20 2 4960 2639 ¦ info@endel.com.eg |
| 26 | Jotun Paints Egypt | Madinaty & Group Projects | Approved Protective Coatings Vendor | Exterior Weatherproof Paint, Interior Finishes & Marine Protective Coatings | +20 2 2405 1800 ¦ jotun.egypt@jotun.com |
| 27 | Bauer Egypt | Cairo Corporate HQ | Specialized Foundation Contractor | Deep Piling, Diaphragm Walls & Heavy Earth Retention Systems | +20 2 2414 1160 ¦ info@bauer.com.eg |
| 28 | Power Axes Piling & Foundation LLC | Cairo Regional Projects | Deep Foundations Subcontractor | Bored Concrete Piles, Sheet Piling & Ground Dewatering Operations | +20 10 0698 1691 ¦ contact@poweraxes.com |
| 29 | GEMS Egypt for Education Services | Al Rehab & Madinaty | Institutional Education Partner | International School Campus Development & Social Infrastructure Operation | +20 2 2160 7220 ¦ info@gems.com.eg |
| 30 | First Design for Urban Investment SAE | Madinaty | Land Co-Development Partner | Commercial Land Parcel Co-Investment & Urban Planning Alignment | +20 2 3345 6003 ¦ corporate@firstdesign.com |
| 31 | Thabat Construction | Banan City (Riyadh, KSA) | Regional Contracting JV Partner | Saudi Turnkey Construction, Residential Villa Clusters & Civil Infrastructure | +966 11 462 7700 ¦ info@thabat.com |
| 32 | Emileo Interiors | Group Commercial Projects | Affiliated Interior Contractor | Specialized Woodwork, Gypsum Ceilings & Premium Interior Architecture | Commercial Fit-Out Directory |
| 33 | MCBS - Modern Construction of Building Systems | Group Infrastructure & Facilities | Group Captive MEP Subsidiary | Electromechanical Systems, Low-Current Networks & Substation Maintenance | +20 2 2693 1643 ¦ mcbs@tmg.com.eg |
| 34 | Orion Facilities Management & Services | Madinaty, The Spine, Al Rehab | Group Central FM Operator | Integrated City Facilities Management, Utilities Operation, Landscaping & Security | +20 10 1110 6286 ¦ info@orion-fm.com |
| 35 | Arab Company for Projects & Urban Development (APUD) | Madinaty & Al Rehab | Master Asset Development Subsidiary | Master Landholding & Developer Entity for Madinaty and Al Rehab Integrated Cities | +20 2 2000 3331 ¦ info@tmg.com.eg |
| 36 | Arab Company for Urban Investment | Noor City | Project Asset SPV Entity | Legal Titleholder & Investment Vehicle for Noor Smart City (Capital Gardens) | +20 2 2000 3331 ¦ info@tmg.com.eg |
| 37 | Nova Park Cairo | Four Seasons Nile Plaza (Cairo) | Hospitality Asset Subsidiary | Asset-Owning Entity for Four Seasons Hotel Cairo at Nile Plaza & Luxury Residencies | +20 2 2000 3331 ¦ hospitality@tmg.com.eg |
| 38 | Egyptian Co. for Development & Real Estate Projects | Four Seasons Sharm El Sheikh | Hospitality Asset Subsidiary | Asset-Owning Entity for Four Seasons Resort Sharm El Sheikh Expansion Packages | +20 2 2000 3331 ¦ hospitality@tmg.com.eg |
| 39 | San Stefano Company for Touristic Investment | San Stefano Grand Plaza (Alexandria) | Hospitality Asset Subsidiary | Asset-Owning Entity for Four Seasons Hotel Alexandria at San Stefano | +20 3 581 8000 ¦ sanstefano@tmg.com.eg |
| 40 | Talaat Moustafa Group Holding S.A.E. (TMGH) | Master Corporate Holding | Ultimate Holding Parent Entity | Central Governance, Treasury, Corporate Finance & Master Brand Ownership | +20 2 2000 3331 ¦ ir@tmg.com.eg |
| 41 | ACE Moharram Bakhoum | SQUARE Mixed-Use & Group Infrastructure | Lead Structural & Bridge Consultant | Structural Engineering Design, Infrastructure Bridges & Site Supervision | +20 2 3301 6701 ¦ ace@ace-mb.com |
| 42 | Atrium Project Management (APM) | Group Institutional Operations | Affiliated Project Management Practice | Project Planning, Construction Cost Management & Technical Contract Review | +20 2 2693 1643 ¦ apm@atriumqc.com |

## Table 12: Key Technical Leadership Registry (38 Leaders)

| Ref ID | Assigned Project / Facility | Executive / Engineer Name | Verified Professional Role | Corporate Employer | Verification Grade |
| --- | --- | --- | --- | --- | --- |
| 1 | SouthMed | Ahmed Ayman | Interior Project Manager | Concrete Plus | Grade A (Primary Record) |
| 2 | Concrete Plus Mega-Projects | Ahmed Khashaba, PMP, PMI-RMP | Senior Project Manager / Construction Planning | Concrete Plus | Grade A (Primary Record) |
| 3 | Concrete Plus Infrastructure | Ayman Tantawy | Executive Construction Director | Concrete Plus | Grade B (Verified Public Profile) |
| 4 | Concrete Plus Civil Works | Kareem Eldsoky, PMP, PE | Senior Project & Quality Assurance Manager | Concrete Plus | Grade A (Primary Record) |
| 5 | Concrete Plus Mega-Projects | Fady Mahfouz Youssef | Senior Electromechanical Commercial Manager | Concrete Plus | Grade A (Primary Record) |
| 6 | Four Seasons Cairo / Madinaty | Ahmed Assaf | Senior Civil Site Engineer | Atrium Quality Contractors | Grade B (Verified Public Profile) |
| 7 | Atrium Commercial Operations | Ahmed El Sobky | Project Controls & Field Operations Lead | Atrium Quality Contractors | Grade B (Verified Public Profile) |
| 8 | Atrium Quality Projects | Mostafa Abdelatty | Senior Quantity Surveying & Cost Engineer | Atrium Quality Contractors | Grade B (Verified Public Profile) |
| 9 | Four Seasons Luxor | Amr A. | Senior Civil Engineer (Luxury Hospitality) | Atrium Quality Contractors | Grade B (Verified Public Profile) |
| 10 | FS Madinaty Villas & FS Luxor | Anas Reda, PMP | Senior Construction Project Manager | Atrium Quality Contractors | Grade A (Primary Record) |
| 11 | The Strip Commercial / Madinaty | Abdelrahman Saeed | Site Operations & QA/QC Engineer | Atrium Quality Contractors | Grade B (Verified Public Profile) |
| 12 | All Seasons Park Mall / Madinaty | Mahmoud El Najjar | Site Section Head Engineer | Atrium Quality Contractors | Grade A (Primary Record) |
| 13 | Privado Luxury Enclave / Madinaty | Youssef Sameh | Senior Project Planning & Scheduling Engineer | Atrium Quality Contractors | Grade A (Primary Record) |
| 14 | Four Seasons Luxor (MEP CP02) | Mahmoud Abd Elaal | Senior Electromechanical Project Engineer | Atrium-CCCE JV | Grade B (Verified Public Profile) |
| 15 | Four Seasons Luxor (MEP CP02) | Khaled Hesham | Site Electromechanical Coordination Engineer | Atrium-CCCE JV | Grade B (Verified Public Profile) |
| 16 | Four Seasons Luxor (MEP CP02) | Sameh El Naggar | Mechanical Systems Site Engineer | Atrium-CCCE JV | Grade B (Verified Public Profile) |
| 17 | Four Seasons Luxor (MEP CP02) | Mohyeeldin Kotb | Cost Control & Estimation Engineer | Atrium-CCCE JV | Grade A (Primary Record) |
| 18 | Four Seasons Luxor (MEP CP02) | Mohamed Yasser | Junior Electromechanical Site Engineer | Atrium-CCCE JV | Grade B (Verified Public Profile) |
| 19 | Four Seasons Luxor | Samer Gobran | Senior Structural Field Engineer | ELEVATE Construction / Atrium | Grade B (Verified Public Profile) |
| 20 | Four Seasons Luxor | Mohamed Karam | Project Management Consultant (Hill International) | Hill International | Grade A (Primary Record) |
| 21 | Noor Smart City | Mohammed Ali, MBA, PMP | Senior Construction Planning Lead | Atrium Project Management (APM) | Grade A (Primary Record) |
| 22 | Noor Smart City | Sherif Nabil, PRMG | Development Project Director | Atrium Project Management (APM) | Grade A (Primary Record) |
| 23 | Noor Smart City | Mahmoud Solyman | Senior Infrastructure Civil Engineer | Atrium Project Management (APM) | Grade A (Primary Record) |
| 24 | Noor Smart City | Alaa Badr | Site Technical Engineer (Civil Infrastructure) | Atrium Project Management (APM) | Grade B (Verified Public Profile) |
| 25 | Madinaty Central Park Extension | Haytham Ahmed Kadry | Master Project Manager (TMG Developments) | TMG Developments | Grade A (Primary Record) |
| 26 | Madinaty Waterpark Package | Fadel Mosaad | Senior Mechanical Commercial Engineer | Atrium Quality Contractors | Grade A (Primary Record) |
| 27 | Madinaty & Noor City Utilities | Farid Emile | MEP Operations General Manager | MCBS (TMG MEP Subsidiary) | Grade A (Primary Record) |
| 28 | MCBS Infrastructure Packages | Adel Yassin, PMP | Lead Electromechanical Systems Engineer | MCBS (TMG MEP Subsidiary) | Grade A (Primary Record) |
| 29 | Madinaty Central Facilities | Tamer Ahmed | Senior Facilities Management Director | Orion Facilities Management | Grade A (Primary Record) |
| 30 | Atrium Corporate Leadership | Hagar Sabry, PRMG, MBA | Executive Project Controls & Operations Director | Atrium Quality Contractors | Grade B (Verified Public Profile) |
| 31 | Four Seasons Cairo Capital | Ali Elkady | Technical Office Field Engineer | Atrium Quality Contractors | Grade B (Verified Public Profile) |
| 32 | Atrium Multi-Site Packages | Mahmoud Elbakry | Senior Quantity Surveying Engineer | Atrium Quality Contractors | Grade B (Verified Public Profile) |
| 33 | Madinaty Commercial Packages | Bassel Nabil, PMP, CCP | Senior Cost Control & Certified Cost Professional | Atrium Quality Contractors | Grade A (Primary Record) |
| 34 | Atrium Commercial & QS Division | Fadel Mosaad | Senior Mechanical Commercial Lead | Atrium Quality Contractors | Grade A (Primary Record) |
| 35 | Atrium Talent & Mobilization | Hoda Hussein | Technical Mobilization & Human Capital Director | Atrium Quality Contractors | Grade B (Verified Public Profile) |
| 36 | TMG New Capital & Madinaty | Amir Elnabawy | Quantity Surveyor & Technical Office Lead | TMG Holding | Grade A (Primary Record) |
| 37 | TMG Corporate Executive Board | Hesham Talaat Moustafa | Chief Executive Officer & Managing Director | TMG Holding | Grade A (Official Corporate Disclosure) |
| 38 | TMG Corporate Executive Board | Tarek Talaat Moustafa | Chairman of the Board of Directors | TMG Holding | Grade A (Official Corporate Disclosure) |

## Table 13: Pre-Contractual Forensic Audit Checklist (10 Gates)

| Gate ID | Risk Category | Audit Verification Procedure | Acceptance Threshold Criteria | Fatal Red Flag Trigger | Mandatory Contractual Protective Clause |
| --- | --- | --- | --- | --- | --- |
| GATE-01 | Contractual Privity | Examine direct contracting entity in relation to master land title deed | Direct contract with land-owning SPV or tripartite guarantee from TMG Holding | Subcontract with ACC/Atrium containing full liability disclaimer for TMG Holding | Parent Company Joint Guarantee & Direct Arbitration Joinder Clause |
| GATE-02 | Payment Instrument | Verify method of disbursement for approved Interim Payment Certificates | Electronic direct wire transfer within 30 days of consultant signature | Post-dated commercial cheques exceeding 90 days maturity | Prompt Payment Clause with 2% monthly commercial late interest penalty |
| GATE-03 | Inflation Indexing | Review price fluctuation clauses against official CAPMAS construction indexes | Automated monthly adjustment for steel, cement, diesel, and foreign exchange | Firm fixed-price lump-sum contract with zero currency adjustment clauses | Mandatory FIDIC Cl. 13.8 Price Fluctuation Formula linked to Central Bank rates |
| GATE-04 | Advance Payment | Check mobilization advance payment terms and bank guarantee conditions | 20% upfront advance payment secured by standard commercial bank guarantee | Advance payment amortized at 100% against initial 3 IPC certificates | Proportional Amortization Clause matching percentage of physical completion |
| GATE-05 | Variation Orders | Review formal change order instruction and valuation mechanisms | Written instruction with approved unit rates prior to physical execution | Oral instructions from site engineers with retrospective claim verification | Pre-Execution Rate Agreement Clause; right to suspend unpriced variations |
| GATE-06 | Dispute Resolution | Evaluate arbitration jurisdiction, seat, and preliminary filing costs | CRCICA arbitration seated in Cairo; English language; sole arbitrator option | Sole jurisdiction granted to summary domestic courts without arbitration clause | Bilateral Multi-tier Dispute Adjudication Board (DAB) before CRCICA referral |
| GATE-07 | Material Import | Review customs clearance risk and foreign exchange letter of credit backing | Employer opens back-to-back LC for imported MEP and plant equipment | Contractor bears full customs clearance risk and unofficial FX spread costs | Employer Import Agency Clause & Direct Central Bank Hard Currency Allocation |
| GATE-08 | Retention Release | Audit conditions governing release of final 5% to 10% retention funds | 50% released at Provisional Handover (TOC); 50% upon Defect Liability (12 mos) | Retention release contingent upon master city handover or NUCA approval | Strict Time-Barred Retention Release Clause backed by Bank Retention Bond |
| GATE-09 | Subcontractor Liens | Examine contractor right to register commercial pledges or liens on works | Contractor retains statutory right of retention over unfinished structures | Unconditional waiver of Article 1138 lien rights under Egyptian Civil Code | Express Preservation of Statutory Lien & Possessory Rights pending payment |
| GATE-10 | Termination Rights | Assess contractor termination triggers upon employer prolonged default | Right to suspend works after 45 days non-payment; termination after 90 days | Contractor prohibited from suspension; heavy contractual delay penalties | Reciprocal Default & Demobilization Compensation Clause with liquidated damages |